## bugs
Bug List
P0 = crash bug, P1 = game stopping but not crash, P2 = not working as expected, P3 = annoying, P4 = nice to have, P5 = future release
# | Reported Date (yyyy-mm-dd) | Reported By | Severity [P0-P5] | Status [Open, in-Progress, Resolved, Won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
0 | 2025-02-22 | Leo | P5 | W | N/A | Example bug | N/A | N/A | N/A
1 | 2025-02-21 | Victor | P2 | R | Victor | Inventories not reloading properly | When a player closes the game, their inventory is persisted and the inventory is re-associated to the player when they relaunch | When a player closes the game, their inventory is persisted but the inventory is not re-associated to the player when they relaunch | 1. Pick up an item in the forest 2. Close the game with ESC 3. Check build/game_state.json 4. Relaunch and pickup another item 5. Close game with ESC 6. When you check build/game_state.json, note how there are two different (player inventory) objects in the inventories array instead of one single object
2 | 2025-02-22 | Steph | P1 | R | Steph | Restarting game in grotto puts player out of bounds | When restarting game in grotto, player should respawn in original forest position | Player spawns out of bounds at the top left when restarting in the grotto | Press R while inside grotto
3 | 2025-02-22 | Victor | P3 | R | Steph | Items can respawn in different biomes | When you pick up an item in the forest, it should only reappear in the forest after the spawn cooldown | When you pick up an item in the forest, it may also re-appear in the grotto after spawn cooldown | 1. Pick up an item in the forest 2. Enter the grotto before the item respawn timer expires 3. The item reappears in the grotto
4 | 2025-02-15 | Leo | P4 | W | Michelle | Possible render layer performance issues | Entities should be sorted according to render layer on insertion, with only dynamic entities being sorted every frame | All entities are sorted every frame, may slow down game with more entities in future | N/A, this is an internal nice to have
5 | 2025-02-22 | Steph | P5 | R | Steph | Leaving grotto | Player should be able to press "F" to leave grotto when near entrance | Player cannot leave grotto | 1. Enter the grotto 2. Try to leave the grotto. You can't.
6 | 2025-03-02 | Steph | P3 | R | Michelle | Can't move along available axis after collision | If a player hits the wall above them while pressing W and D, they should not be able to move upwards anymore but can still glide along to the right | Player's movement is completely stopped | Move diagonally towards the hitbox of an obstacle
7 | 2025-03-09 | Steph | P2 | R | Steph | Can shoot through obstacles | If a player throws ammo at terrain, it should collide with the tree and be removed from screen | The ammo doesn't disappear on collision | 1. Pick up a fruit 2. Select the fruit in inventory 3. Throw it at a tree 4. It continues moving through the tree
8 | 2025-03-09 | Corina | P4 | R | Victor / Leo | The cauldron menu can have an X button in the top corner so users know how to close it. Right now pressing F to close it isn’t very intuitive. | Visible "X" sign at top corner, click to exit the cauldron menu | Player can only press F key to close the menu. | 1. Go to grotto 2. Open the cauldron menu
9 | 2025-03-09 | Victor | P3 | R | Corina | Item collection UI boxes re-appear for a few frames upon item regeneration | Item regenerates without other UI elements, if the player isn't nearby | Item regenerates with the '[F] (item name)' text box, if the player isn't nearby | 1. Pick up a magical fruit 2. Step far away and wait a few seconds 3. Upon regenerating, the magical fruit will appear with a box saying '[F] Magical Fruit'
10 | 2025-03-09 | Stephanie | P4 | W | Stephanie | Refactor the tutorial system to be better | N/A | N/A | N/A
11 | 2025-03-09 | Steph | P2 | R | Stephanie | Cauldron item count doesn't register correctly | Adding 5 coffee beans and 3 magical fruits should trigger the ladle tutorial. | Adding 5 coffee beans and 3 magical fruits does not trigger the ladle tutorial, it may be fewer or more than the requested amount that triggers the tutorial | Occasionally happens - has to do with serialization 1. Collect 5 coffee beans and 3 magical fruits 2. Proceed through the tutorial until the step where it asks you to add ingredients into the cauldron 3. Attempt to add all items
12 | 2025-03-09 | Steph | P2 | O | Leo | Adding item to cauldron removes multiple counts from player inventory | Only one count of the item should be dropped into the item at a time | Sometimes dragging one item to cauldron will remove multiple counts of it | Doesn't always happen 1. Drag items into the cauldron
13 | 2025-03-09 | Corina | P3 | R | Corina | Item dropped by enemy should not respawn | Sap and Magical Dust should not respawn | They respawn | 1. Kill the enemy 2. Pick up the item
14 | 2025-03-10 | Steph | P0 | R | Steph | Re-opening a cauldron produces an assert error | A cauldron should be able to be re-opened and should be the same entity that was created when the game started | Entity not in registry error | 1. Open a cauldron 2. Restart the game - immediate error 3. Or leave the grotto and re-enter 4. Try opening the cauldron again
15 | 2025-03-10 | Leo | P0 | R | Leo | Drag empty slot into cauldron causes crash | Dragging empty slot into cauldron should not do anything | Dragging empty slot into cauldron causes reference outside of array bounds and may crash the game | 1. Open a cauldron 2. Try to drag a slot with no items and drop it into the cauldron
17 | 2025-03-10 | Steph | P4 | R | Leo | While stirring, the ladle can appear anywhere on the screen | When stirring, the ladle should stay within the bounds of the cauldron even if the mouse moves out of bounds | Ladle follows mouse around the screen | 1. Open cauldron menu 2. Pick up ladle and try to stir
18 | 2025-03-10 | Steph | P2 | R | Steph | The player can be killed while on switching biome | When player switches biomes, all motion stops | Enemies and ammo can continue moving during a biome switch | 1. Enter desert biome 2. Guide a mummy towards the forest entrance 3. Attempt to switch biome and the mummy will still be moving and if close enough to player, will kill them
19 | 2025-03-13 | Leo | P3 | R | Victor | Duplicate game_state.json files | There should only be one game_state.json file | There are multiple game_state.json files, different game saves may load the game depending on the instantiation | 1. Start game in main directory with ./run.sh or .\run.bat 2. Close the game 3. Start the game from the Build directory 3. Close the game - should see 2 different game_state files
20 | 2025-03-23 | Steph | P2 | O | Steph | Incorrect health on reset | Player's health always reset to max on death | Player's health doesn't always reset to max on death - instead about 70% | 1. go to the deep forest 2. Go to the tree enemies 3. Get hit until you die 4.Check your health on respawn
21 | 2025-03-23 | Steph | P3 | O | Leo/Victor | Inventory item stacking | Items should stack | The same item doesn't stack | 1. Collect a bunch of galefruits 2. Sometimes one ends up in a new stack

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release

## Backlog
Project Backlog
# | Reported By | Severity [P0-P5] | Status [Open, in-Progress, Resolved, Won't fix] | Assigned To | Description
1 | Corina | P4 | O | Victor / Leo | The cauldron menu can have an X button in the top corner so users know how to close it. Right now pressing F to close it isn’t very intuitive.
2 | Stephanie | P4 | O | Stephanie | Refactor the tutorial system to be better
3 | Stephanie | P4 | R | Corina | Make it so that you don't have to drag the pestle into the bowl in order to grind
4 | Leo | P4 | R | Stephanie | Cauldron continues boiling once you re-enter cauldron
5 | Stephanie | P4 | O | Victor | Cauldron serialization
6 | Michelle | P4 | O |  | Have a timer of indicator to show the duration of the potion
7 | Leo | P4 | O | Stephanie | Stack potion effects
8 | Leo | P4 | O |  | Add chest / garbage can
9 | Victor | P4 | O |  | Change tenacity potion or change inventory
10 | Stephanie | P4 | R | Stephanie | Serialize active effects
11 | Stephanie | P4 | O |  | Fix enemy collision detection
12 | Stephanie | P4 | O | Michelle | Change the in-between biome drawing thingy? like the forest to mushroom
13 | Michelle | P4 | O | Victor | Have the actual potion instead of perfect quality color
14 | Michelle | P4 | O | Michelle | Having a title screen for the game like Enchanted Grotto, Play, load
15 |  |  |  |  | Only be able to turn page if at lecturn, otherwise can only see current page
16 |  |  |  |  | Respawn counter containues